FOR TRAINING USE ONLY — FICTITIOUS DOCUMENT
This contract was invented for an AI training exercise. The parties, site, figures and terms are illustrative only and do not represent any real agreement. Do not rely on it for any commercial or legal purpose.

AGREEMENT FOR

CIVIL, STRUCTURAL AND BUILDING WORKS

Process Building

BepsiCo Manufacturing Facility Expansion

MIDC Chakan Industrial Area, Phase II, Pune, Maharashtra

between

BEPSICO INDIA MANUFACTURING PRIVATE LIMITED

(the "Employer")

and

ROHAN BUILDERS PRIVATE LIMITED

(the "Contractor")

| Contract No. | BPC/CHK/PB/2026/014 |
| --- | --- |
| Date of Agreement | 12 March 2026 |
| Letter of Award | 28 February 2026 |
| Contract type | Lump sum, firm price |

# CONTRACT DATA

The following particulars summarise the key commercial terms. In case of conflict, the Clauses of this Agreement prevail.

| Item | Particulars | Clause |
| --- | --- | --- |
| Employer | BepsiCo India Manufacturing Private Limited | — |
| Contractor | Rohan Builders Private Limited | — |
| Employer's Representative | Project Director, BepsiCo Projects Division (or the appointed project management consultant) | 2.4 |
| Site | Plot D-27, MIDC Chakan Industrial Area, Phase II, Pune 410501 | — |
| Contract Price | INR 148.60 Crore (INR 1,48,60,00,000), excluding GST | 3.1 |
| Price adjustment | Reinforcement steel and cement only, beyond ±5% of the Base Date index | 3.3 |
| Base Date | 10 February 2026 | 1.1(b) |
| Commencement Date | 01 April 2026 | 4.1 |
| M1 – Piling complete | 31 July 2026 | 4.2 |
| M2 – Superstructure complete | 30 November 2026 | 4.2 |
| M3 – Mechanical Completion | 15 February 2027 | 4.2 |
| Taking Over | 31 March 2027 | 4.2 |
| Delay damages (M3) | 0.5% of Contract Price per week; maximum 10% of Contract Price | 7.1, 7.2 |
| Interim delay damages (M2) | 0.1% of Contract Price per week | 7.3 |
| Mobilisation advance | 10% of Contract Price against bank guarantee; recovered at 12.5% of each bill | 9.1 |
| Payment period | 45 days from certification | 9.3 |
| Retention | 5% of each interim payment; 50% released at Taking Over | 10 |
| Performance security | 10% of Contract Price, valid until 90 days after the Defects Liability Period | 11 |
| Defects Liability Period | 24 months from Taking Over; 10-year waterproofing warranty | 12 |
| Contractor's liability cap | 100% of Contract Price (with exceptions) | 14.2 |
| Disputes | Senior representatives, then arbitration (seat: Pune) | 19 |
| Governing law | Laws of India | 20 |

# AGREEMENT

THIS AGREEMENT is made at Pune on 12 March 2026

BETWEEN

BEPSICO INDIA MANUFACTURING PRIVATE LIMITED, a company incorporated under the Companies Act, 2013, acting through its authorised signatory (the "Employer", which expression shall include its successors and permitted assigns);

AND

ROHAN BUILDERS PRIVATE LIMITED, a company incorporated under the Companies Act, 2013, acting through its authorised signatory (the "Contractor", which expression shall include its successors and permitted assigns).

The Employer and the Contractor are each a "Party" and together the "Parties".

## RECITALS

A.	The Employer is expanding its manufacturing facility at MIDC Chakan Industrial Area, Phase II, Pune, and requires the construction of a new Process Building (the "Project").

B.	The Employer invited tenders under Enquiry No. BPC/CHK/ENQ/2025/088. The Contractor submitted its offer dated 20 January 2026 and, following negotiations, the Employer issued a Letter of Award dated 28 February 2026.

C.	The Parties wish to record the terms on which the Contractor shall execute and complete the Works.

NOW, THEREFORE, THE PARTIES AGREE AS FOLLOWS:

# 1.  DEFINITIONS AND INTERPRETATION

1.1	In this Agreement the following words and expressions have the meanings given below:

(a)	"Agreement" or "Contract" means this agreement, its Annexures and the documents listed in Clause 1.3.

(b)	"Base Date" means 10 February 2026, being 28 days before the latest date for submission of the Contractor's final offer.

(c)	"Contract Price" means the lump sum of INR 1,48,60,00,000 (Indian Rupees One Hundred Forty-Eight Crore Sixty Lakh only), exclusive of GST, subject to adjustment only as expressly provided in this Agreement.

(d)	"Employer's Representative" means the person appointed by the Employer under Clause 2.4 to act on its behalf.

(e)	"Hold Point" means a stage of the Works identified in Annexure B beyond which the Contractor shall not proceed without the written release of the Employer's Representative.

(f)	"Mechanical Completion" means the stage at which the Works are complete to the extent that the Employer's process equipment can be installed, including all equipment foundations, the ground-floor industrial slab, suspended slabs, roof, cladding and safe access, as certified by the Employer's Representative. Minor items that do not affect installation may remain on a punch list.

(g)	"Milestone" and "Milestone Date" mean the milestones and dates set out in Clause 4.2 and Annexure C.

(h)	"Programme" means the Contractor's Level 3 programme approved under Clause 5.

(i)	"Taking Over" means the issue of the Taking-Over Certificate under Clause 4.4 on completion of all the Works, including finishes, external works and handover documentation.

(j)	"Variation" means a change to the Works instructed in accordance with Clause 8.

(k)	"Works" means all civil, structural and building works described in Annexure A, including temporary works.

1.2	Headings are for convenience only. A reference to a law includes that law as amended, re-enacted or replaced from time to time. "Days" means calendar days.

1.3	The documents forming the Contract are to be read as mutually explanatory. In case of conflict, they shall take precedence in the following order: (a) this Agreement; (b) the Letter of Award dated 28 February 2026; (c) Annexure C (Milestones, Delay Damages and Payment Breakdown); (d) Annexure B (Key Technical Specifications) and the Employer's drawings; (e) Annexure A (Scope of Works); (f) the Contractor's offer dated 20 January 2026, as clarified in negotiations.

# 2.  SCOPE AND GENERAL OBLIGATIONS

2.1	The Contractor shall execute and complete the Works and remedy any defects in them in accordance with the Contract, the Employer's drawings and specifications, the applicable Indian Standards and good industry practice. The Contractor is responsible for the design of all temporary works.

2.2	The Contractor is deemed to have inspected the Site and its surroundings and the Employer's geotechnical investigation report (Ref. GIR/CHK/2025/07), and to have satisfied itself as to ground and sub-surface conditions, including rock levels, groundwater and monsoon run-off. No claim for time or money shall be admissible for ground conditions, except for conditions which an experienced contractor could not reasonably have foreseen at the Base Date.

2.3	The Contractor shall provide builder's works in connection with mechanical, electrical and process installations by others, and shall coordinate with and give reasonable access to the Employer's other contractors without additional cost.

2.4	The Employer shall appoint the Employer's Representative and notify the Contractor in writing. An instruction is valid only if given in writing by the Employer's Representative.

2.5	The Employer shall issue good-for-construction (GFC) drawings in accordance with the drawing schedule agreed with the Programme.

2.6	The Employer shall obtain building permission from MIDC and the Consent to Establish from the Maharashtra Pollution Control Board. The Contractor shall obtain all other permits, licences and registrations required for execution, including labour licences, registration of the establishment and workers under applicable labour laws, and permissions for dewatering and the use of public roads.

# 3.  CONTRACT PRICE

3.1	The Contract Price is a firm lump sum for the complete Works and includes all labour, materials, plant, temporary works, overheads, profit, insurance, taxes and duties (other than GST), and all risks and obligations under the Contract.

3.2	GST shall be paid by the Employer at the applicable rate against valid tax invoices. Any change in the rate of GST after the Base Date shall be adjusted at actuals.

3.3	Price adjustment applies only to reinforcement steel and cement, using the Wholesale Price Index for the respective commodity published by the Office of the Economic Adviser, DPIIT, Government of India. An adjustment shall be made only to the extent that the index for the month of consumption differs from the Base Date index by more than ±5%. No adjustment applies to any other input, including labour, fuel, aggregates or structural steel.

3.4	Quantities in the bill of quantities are indicative only. The Contractor shall have no claim for any change in quantities within the lump sum scope unless it arises from a Variation.

# 4.  TIME FOR COMPLETION AND MILESTONES

4.1	The Contractor shall commence the Works on 01 April 2026 (the "Commencement Date") and shall proceed with due expedition and without delay.

4.2	The Contractor shall achieve the following Milestones by the Milestone Dates:

| No. | Milestone | Milestone Date |
| --- | --- | --- |
| M1 | Piling complete; all pile test reports approved | 31 July 2026 |
| M2 | Superstructure complete: RCC frame and post-tensioned slabs up to roof level | 30 November 2026 |
| M3 | Mechanical Completion | 15 February 2027 |
| TO | Taking Over of the whole of the Works | 31 March 2027 |

4.3	Time is of the essence for Milestones M2 and M3 and for Taking Over.

4.4	When the Contractor considers the Works complete, it may apply for a Taking-Over Certificate. Within 14 days the Employer's Representative shall either issue the certificate or list the work remaining to be done.

4.5	The Employer may use any part of the Works before Taking Over, including for the installation of process equipment. Such use shall not amount to Taking Over of that part unless so certified.

# 5.  PROGRAMME, PROGRESS AND ACCELERATION

5.1	Within 21 days of the Commencement Date, the Contractor shall submit a resource-loaded Level 3 Programme in Primavera P6 (native .xer format) showing the critical path, all Milestones and Hold Points, drawing requirements and the procurement of long-lead items.

5.2	By the 5th of each month the Contractor shall submit a progress report and an updated Programme, with a three-week look-ahead and a narrative of delays and recovery measures.

5.3	If progress on the critical path falls more than 14 days behind the approved Programme for reasons that do not entitle the Contractor to an extension of time, the Contractor shall, on notice from the Employer's Representative, submit and implement a recovery plan at its own cost, including additional shifts, resources and plant.

5.4	The Employer may request the Contractor to achieve any Milestone earlier than its Milestone Date. Within 7 days of such a request the Contractor shall submit an acceleration proposal stating the measures, the revised dates and the cost. The Contractor shall be entitled to payment for acceleration only where the proposal, including its cost, has been accepted in writing by the Employer's Representative before the Contractor commences the accelerated measures. Any acceleration undertaken without such prior written acceptance, including in response to any request, correspondence, meeting minutes or proposal of the Employer, shall be deemed to be at the Contractor's own cost and risk.

5.5	On acceptance of an acceleration proposal, the revised dates shall replace the relevant Milestone Dates for all purposes of the Contract, including delay damages under Clause 7.

5.6	Night work involving concrete pours requires 48 hours' notice to the Employer's Representative and compliance with applicable noise limits and MIDC conditions.

# 6.  EXTENSION OF TIME

6.1	The Contractor shall be entitled to an extension of the relevant Milestone Dates if and to the extent that completion is or will be delayed by:

(a)	a Variation;

(b)	any delay, impediment or prevention caused by the Employer, the Employer's Representative or the Employer's other contractors;

(c)	issue of GFC drawings more than 7 days after the date in the agreed drawing schedule;

(d)	Force Majeure under Clause 18;

(e)	a change in law under Clause 15; or

(f)	a suspension instructed by the Employer that is not due to the Contractor's default.

6.2	The Contractor shall give notice to the Employer's Representative, describing the event, within 14 days after the Contractor became aware, or should have become aware, of the event. If the Contractor fails to give notice within this period, the Milestone Dates shall not be extended, the Contractor shall not be entitled to any additional payment, and the Employer shall be discharged from all liability in connection with the event.

6.3	Within 28 days of its notice, the Contractor shall submit a fully detailed claim, including a time impact analysis on the approved Programme demonstrating the effect on the critical path.

6.4	Where a delay caused by an event listed in Clause 6.1 is concurrent with a delay for which the Contractor is responsible, the Contractor shall be entitled to an extension of time but not to additional cost.

6.5	The Employer's Representative shall respond within 28 days of receiving the detailed claim.

# 7.  DELAY DAMAGES

7.1	If the Contractor fails to achieve Mechanical Completion by the M3 Milestone Date, it shall pay the Employer liquidated damages at 0.5% of the Contract Price for each week of delay (pro rata for part weeks).

7.2	The total liquidated damages under Clause 7.1 shall not exceed 10% of the Contract Price.

7.3	If the Contractor fails to achieve Milestone M2 by its Milestone Date, it shall pay interim damages at 0.1% of the Contract Price for each week of delay until M2 is achieved. Interim damages are not refundable, even if Mechanical Completion is achieved on or before the M3 Milestone Date, and do not count towards the limit in Clause 7.2.

7.4	The Parties agree that the liquidated damages are a genuine pre-estimate of the Employer's loss. Payment of liquidated damages is without prejudice to the Employer's right to recover general damages for loss exceeding the liquidated damages, including loss of production.

7.5	The Employer may deduct delay damages from any sum due to the Contractor or recover them from the Performance Security.

# 8.  VARIATIONS

8.1	The Employer's Representative may instruct Variations at any time before Taking Over. A Variation is valid only if issued as a written Variation Order signed by the Employer's Representative.

8.2	The Contractor shall not act on oral instructions, meeting minutes or e-mails unless confirmed by a Variation Order. Work executed without a Variation Order shall not be paid for.

8.3	Within 7 days of receiving a Variation Order, the Contractor shall submit its quotation for cost and time. Variations shall be valued: (a) at bill of quantities rates where applicable; (b) at rates derived from those rates for similar work; or (c) failing these, at actual cost plus 12% for overheads and profit.

8.4	A Variation does not entitle the Contractor to an extension of time unless the Contractor demonstrates, through a time impact analysis on the approved Programme, that the Variation affects the critical path.

8.5	The Contractor shall not be entitled to any payment for omitted work, including loss of profit, provided that the aggregate value of omissions does not exceed 15% of the Contract Price.

# 9.  PAYMENT

9.1	The Employer shall pay an interest-free mobilisation advance of 10% of the Contract Price against an unconditional bank guarantee of equal value from a scheduled commercial bank. The advance shall be recovered at 12.5% of the gross value of each interim payment, starting with the first, until fully recovered.

9.2	By the 5th of each month the Contractor shall submit an interim payment application for the work done in the previous month, valued against the payment breakdown in Annexure C, with supporting measurements and quality records.

9.3	The Employer's Representative shall certify each complete application within 14 days of receipt. The Employer shall pay the certified amount within 45 days of certification.

9.4	If payment is delayed by more than 30 days beyond the due date, the Employer shall pay interest at 9% per annum on the delayed amount for the period of delay beyond those 30 days.

9.5	The Employer shall deduct from each payment: tax deducted at source as required by law; labour welfare cess at 1% under the Building and Other Construction Workers' Welfare Cess Act, 1996; retention; recovery of the mobilisation advance; and any other amount due from the Contractor.

9.6	The Employer may set off any sum due from the Contractor under this Contract, or under any other contract between the Contractor and the Employer or its affiliates, against any sum due to the Contractor.

9.7	The Contractor shall submit its final account within 60 days after Taking Over. The Employer's Representative shall issue the final payment certificate within 60 days of receiving it.

# 10.  RETENTION

10.1	The Employer shall retain 5% of the gross value of each interim payment, up to a maximum of 5% of the Contract Price.

10.2	Half of the retention shall be released on Taking Over, and the balance on expiry of the Defects Liability Period once all notified defects have been remedied.

10.3	At the Employer's discretion, retention may be released against an unconditional bank guarantee of equal value.

# 11.  PERFORMANCE SECURITY

11.1	Within 21 days of the Letter of Award, the Contractor shall provide a performance security of 10% of the Contract Price as an unconditional, irrevocable bank guarantee from a scheduled commercial bank, in the Employer's format.

11.2	The performance security shall remain valid until 90 days after the expiry of the Defects Liability Period. The Contractor shall extend its validity at least 30 days before expiry, failing which the Employer may encash it.

11.3	The Employer may encash the performance security for any amount due from the Contractor under the Contract, without prior reference to the Contractor.

# 12.  DEFECTS LIABILITY AND WARRANTIES

12.1	The Defects Liability Period is 24 months from Taking Over. Where a part of the Works is taken over separately, the period for that part runs from its taking over.

12.2	The Contractor shall remedy a notified defect within 7 days, or within 48 hours where the defect affects safety, water-tightness or the Employer's production. If the Contractor fails to do so, the Employer may remedy the defect at the Contractor's cost.

12.3	The Contractor shall provide a 10-year warranty from Taking Over for all roof and below-ground waterproofing, given jointly with the specialist applicator in the Employer's format.

12.4	Nothing in this Clause limits the Contractor's liability for latent defects under applicable law.

# 13.  INSURANCE

13.1	The Contractor shall maintain, in the joint names of the Parties from the Commencement Date until Taking Over, a Contractor's All Risks policy for the Contract Price plus 15% for debris removal and professional fees, including earthquake and storm, tempest, flood and inundation (STFI) cover.

13.2	The Contractor shall maintain third-party liability insurance of at least INR 10 Crore per occurrence, with no limit on the number of occurrences.

13.3	The Contractor shall insure its workers under the Employees' Compensation Act, 1923 and ensure ESI coverage for eligible workers.

13.4	All deductibles shall be borne by the Contractor.

# 14.  INDEMNITY AND LIMITATION OF LIABILITY

14.1	The Contractor shall indemnify the Employer against all claims, damages, losses and expenses arising from death, injury or damage to property caused by the Works, and from any breach of law by the Contractor or its subcontractors.

14.2	The Contractor's total liability under or in connection with the Contract shall not exceed 100% of the Contract Price, except in cases of fraud, wilful misconduct, gross negligence, abandonment of the Works, or liability for death or injury under Clause 14.1.

14.3	Neither Party shall be liable to the other for indirect or consequential loss, including loss of profit, loss of use or loss of contract, save that this Clause 14.3 shall not limit the Employer's right to recover loss of production under Clause 7.4.

14.4	The Employer shall indemnify the Contractor against claims arising from the Employer's use or occupation of the Site and from the negligence of the Employer.

# 15.  CHANGE IN LAW

15.1	If, after the Base Date, there is a change in any law of India, including the introduction of a new law, the repeal or amendment of an existing law, or a change in its official interpretation, and including any by-law, regulation, notification, development control regulation or statutory permit condition, which affects the Contractor's cost or time of performance, the Contract Price and/or the Milestone Dates shall be adjusted accordingly.

15.2	The Contractor shall give notice of a change in law within 28 days after it is published in the Official Gazette or otherwise notified. The consequences in Clause 6.2 apply to any failure to give notice.

15.3	No adjustment shall be made for changes in minimum wages, variable dearness allowance or labour welfare cess, or in any law relating to labour, employment, wages, social security or occupational safety, all of which are at the Contractor's risk.

15.4	The Works shall comply with the Indian Standards and the National Building Code current at the Base Date (Annexure D). Where a revised code is published after the Base Date, the Contractor shall notify the Employer, who may instruct compliance as a Variation. Compliance with a revised code that is made mandatory by law shall be treated as a change in law under Clause 15.1.

# 16.  HEALTH, SAFETY AND ENVIRONMENT

16.1	The Contractor shall comply with all applicable laws, including the Building and Other Construction Workers (Regulation of Employment and Conditions of Service) Act, 1996 and the rules under it, the Contract Labour (Regulation and Abolition) Act, 1970, the Environment (Protection) Act, 1986 and the Construction and Demolition Waste Management Rules, 2016, and with the Employer's HSE Manual.

16.2	The Contractor shall deploy a full-time qualified safety officer on Site and one additional safety supervisor for every 250 workers, and shall operate a permit-to-work system for work at height, excavations, hot work and heavy lifts.

16.3	The Employer may levy a penalty of INR 50,000 per safety violation recorded by the Employer's Representative, deducted from interim payments, and may stop any unsafe activity. A stoppage for safety reasons does not entitle the Contractor to an extension of time or additional cost.

16.4	By 15 May each year the Contractor shall submit a monsoon preparedness plan covering dewatering, drainage of excavations and piling platforms, and protection of materials.

16.5	The Contractor shall report any incident within 24 hours, and any fatal or serious incident within 2 hours.

# 17.  SUSPENSION AND TERMINATION

17.1	The Employer may suspend all or part of the Works by notice. If the suspension is not due to the Contractor's default, the Contractor shall be entitled to an extension of time and to its demonstrable costs.

17.2	The Employer may terminate the Contract on 7 days' notice if the Contractor: (a) abandons the Works or fails to proceed for 14 days; (b) fails to comply with a notice to correct within 14 days; (c) becomes insolvent; (d) assigns the Contract or subcontracts the whole of the Works without consent; or (e) reaches the maximum delay damages under Clause 7.2. The Employer may then complete the Works itself or through others at the Contractor's risk and cost, and encash the performance security.

17.3	The Employer may terminate the Contract at any time for its convenience by giving 30 days' notice. The Contractor shall be paid for work executed, materials delivered to Site and reasonable demobilisation costs, but shall not be entitled to any compensation for loss of anticipated profit or overheads on work not executed.

17.4	The Contractor may terminate the Contract only if the Employer fails to pay a certified amount within 90 days after its due date, by giving 30 days' notice, and only if the amount remains unpaid at the end of that notice.

# 18.  FORCE MAJEURE

18.1	"Force Majeure" means an exceptional event beyond a Party's control, which that Party could not reasonably have provided against before entering into the Contract, and which it could not reasonably have avoided or overcome, including war, riot, an epidemic declared by government, earthquake, flood, cyclone and a government-ordered lockdown.

18.2	Rainfall during the monsoon season (June to September) is not Force Majeure unless the daily rainfall recorded at the India Meteorological Department observatory at Pune (Shivajinagar) exceeds 100 mm on three or more consecutive days. The Contractor is deemed to have allowed for normal monsoon conditions in the Programme.

18.3	The affected Party shall give notice within 7 days of becoming aware of the Force Majeure event, failing which it shall not be entitled to relief.

18.4	Force Majeure entitles the Contractor to an extension of time only, without additional cost.

18.5	If Force Majeure prevents the execution of substantially all the Works for a continuous period of 120 days, either Party may terminate the Contract on 30 days' notice, and the Contractor shall be paid for work done.

# 19.  DISPUTE RESOLUTION

19.1	Any dispute shall first be referred to the Employer's Project Director and the Contractor's Managing Director, who shall meet within 14 days and try in good faith to resolve it within 30 days of the referral.

19.2	Any dispute not so resolved shall be finally settled by arbitration under the Arbitration and Conciliation Act, 1996, by a sole arbitrator appointed by the Managing Director of the Employer.

19.3	The seat and venue of arbitration shall be Pune, and the language shall be English.

19.4	The Contractor shall continue the Works during any dispute, and the Employer shall continue to pay undisputed amounts.

# 20.  GOVERNING LAW AND JURISDICTION

20.1	The Contract is governed by the laws of India. Subject to Clause 19, the courts at Pune shall have exclusive jurisdiction.

# 21.  GENERAL

21.1	Notices shall be in writing and delivered by hand, registered post or e-mail to: for the Employer, the Project Director, BepsiCo Projects Division, Chakan Phase II Site Office, MIDC Chakan, Pune 410501 (projects.chakan@bepsico.example); for the Contractor, the Managing Director, Rohan Builders Private Limited, Pune (contracts@rohanbuilders.example).

21.2	The Contractor shall not assign the Contract. It shall not subcontract more than 40% of the Contract Price by value, or any piling or post-tensioning work, without the Employer's prior written consent.

21.3	The Contractor shall keep confidential all information about the Employer's processes and facility, and shall not photograph the Site or publish any information about the Project without the Employer's consent.

21.4	This Agreement is the entire agreement between the Parties about its subject matter. Any amendment must be in writing and signed by both Parties.

IN WITNESS WHEREOF the Parties have executed this Agreement on the date first written above.

| For and on behalf of BepsiCo India Manufacturing Private Limited | For and on behalf of Rohan Builders Private Limited |
| --- | --- |
| Signature: ______________________________ | Signature: ______________________________ |
| Name: ______________________________ | Name: ______________________________ |
| Designation: ______________________________ | Designation: ______________________________ |
| Date: ______________________________ | Date: ______________________________ |
| Witness: ______________________________ | Witness: ______________________________ |

# ANNEXURE A — SCOPE OF WORKS (SUMMARY)

The Process Building is a ground-plus-two-level structure measuring 120 m × 72 m in plan (footprint about 8,640 m²; built-up area about 25,900 m²). The detailed scope is defined in the Employer's drawings and Technical Specification Volume II (Ref. BPC/CHK/TS/02).

| Ref. | Element | Description |
| --- | --- | --- |
| A1 | Site preparation | Site clearance, grading to formation level, temporary drainage, and a 60 m² site office for the Employer's Representative. |
| A2 | Piling | About 420 bored cast-in-situ piles of 600 mm and 750 mm diameter, socketed into basalt, typical depth 16–20 m; initial and routine load tests; pile integrity tests on all piles. |
| A3 | Foundations | Pile caps, grade beams, sumps, pits and six vibration-isolated block foundations for process machines. |
| A4 | Superstructure | RCC frame in M40 concrete; 250 mm post-tensioned flat slabs at +7.50 m and +15.00 m; staircases, lift cores and pipe-rack supports. |
| A5 | Roof and cladding | Pre-engineered steel building (PEB) roof at +24.00 m with standing-seam insulated roof sheeting, skylights and wall cladding, including design, supply and erection. |
| A6 | Ground-floor slab | 200 mm steel-fibre-reinforced industrial floor to FM2 flatness, designed for 50 kN/m², with epoxy finish in process areas. |
| A7 | Building finishes | Blockwork, plaster, doors, windows, flooring, painting and false ceilings in control rooms. |
| A8 | Waterproofing | Below-ground waterproofing to pits and sumps; membrane waterproofing to RCC canopies and wet areas. |
| A9 | External works | RCC internal roads, storm-water drains and rainwater harvesting within the building zone. |
| A10 | Exclusions | Process equipment, MEP services, fire-fighting systems and electrical substations (by the Employer's other contractors). The Contractor provides builder's works, embedments and coordination. |

# ANNEXURE B — KEY TECHNICAL SPECIFICATIONS

This Annexure summarises key requirements. The full requirements are in Technical Specification Volume II (Ref. BPC/CHK/TS/02).

## B1  Piling

B1.1	Bored cast-in-situ piles to IS 2911 (Part 1/Section 2): 2010, in M35 concrete with a minimum cement content of 400 kg/m³, placed by tremie. Minimum rock socket of 1.5 × pile diameter into hard basalt, confirmed by the Employer's geotechnical engineer.

B1.2	Safe working load in compression: 150 t for 600 mm piles and 230 t for 750 mm piles.

B1.3	Initial load tests: two test piles for each diameter, loaded to 2.5 × safe working load in accordance with IS 2911 (Part 4): 2013, completed before production piling starts.

B1.4	Routine load tests on 0.5% of working piles, loaded to 1.5 × safe working load. Low-strain pile integrity tests on 100% of working piles.

## B2  Concrete

B2.1	Design mixes to IS 10262: 2019. Grades: M40 for columns, beams and slabs; M35 for piles and pile caps; M30 for external works.

B2.2	Maximum water-cement ratio 0.40 for M40. Slump 100 ± 25 mm at the point of placement.

B2.3	Cube sampling frequency per IS 456 Clause 15.2.2; cubes tested at 7 and 28 days; acceptance per IS 456 Clause 16.

B2.4	Minimum 14 days' continuous moist curing for all structural concrete. Concrete temperature at placement shall not exceed 32 °C.

## B3  Reinforcement

B3.1	High-strength deformed bars of grade Fe 550D to IS 1786: 2008 from primary producers approved by the Employer, with mill test certificates for every lot.

B3.2	Nominal cover: piles 75 mm; pile caps 50 mm; columns 40 mm; beams and slabs 30 mm. Ductile detailing to IS 13920: 2016.

## B4  Post-tensioned slabs

B4.1	250 mm bonded post-tensioned flat slabs to IS 1343: 2012, using low-relaxation 7-wire strands to IS 14268 in flat galvanised ducts.

B4.2	Stressing only when site-cured cubes reach 25 N/mm². Measured elongations must be within ±7% of calculated values; otherwise stressing stops pending review. Ducts shall be grouted within 7 days of stressing.

B4.3	No drilling, coring or fixing into post-tensioned slabs without locating tendons by scanning and obtaining written approval.

## B5  Industrial ground-floor slab

B5.1	200 mm steel-fibre-reinforced ground-bearing slab in M35 concrete, with a minimum fibre dosage of 30 kg/m³, on a 150 mm compacted granular sub-base with a 250-micron separation membrane.

B5.2	Surface regularity to FM2 in accordance with Concrete Society Technical Report 34 (4th Edition), surveyed within 7 days of placing. Non-compliant areas shall be ground or replaced at the Contractor's cost.

B5.3	Saw-cut contraction joints at a maximum of 6 m centres, cut within 12 to 18 hours of placing.

## B6  Roofing, waterproofing and monitoring

B6.1	PEB roof designed to IS 800: 2007 and IS 875 (Part 3): 2015 for a basic wind speed of 39 m/s.

B6.2	All waterproofed areas shall pass a 48-hour flood test before being covered.

B6.3	Settlement monitoring points on all perimeter columns, read fortnightly until Taking Over. Alert level: 10 mm total settlement or 1 in 1,000 differential settlement. Action level: 20 mm total settlement, at which point work above the affected area stops pending review.

## B7  Summary of Hold Points

| HP | Stage | Release required before |
| --- | --- | --- |
| HP-1 | Initial pile load test reports approved | Production piling |
| HP-2 | Pile integrity test report for the pile group approved | Concreting the pile cap |
| HP-3 | Reinforcement, formwork and embedments inspected (pour card signed) | Any structural concrete pour |
| HP-4 | Post-tensioning stressing records approved | Removing back-props and formwork |
| HP-5 | Floor flatness survey approved | Installing process equipment |

# ANNEXURE C — MILESTONES, DELAY DAMAGES AND PAYMENT BREAKDOWN

## C1  Milestones and delay damages

| No. | Milestone | Date | Delay damages | Reference |
| --- | --- | --- | --- | --- |
| M1 | Piling complete; all pile test reports approved | 31 Jul 2026 | None | Monitored in progress reports |
| M2 | Superstructure complete: RCC frame and PT slabs to roof level | 30 Nov 2026 | 0.1% of Contract Price per week (INR 14.86 lakh) | Clause 7.3 |
| M3 | Mechanical Completion | 15 Feb 2027 | 0.5% of Contract Price per week (INR 74.30 lakh) | Clauses 7.1, 7.2 (max INR 14.86 Crore) |
| TO | Taking Over: all Works, finishes and as-built documents | 31 Mar 2027 | None | Retention release, Clause 10.2 |

## C2  Payment breakdown

Interim payments are valued against the following breakdown of the Contract Price.

| Ref. | Work package | % of price | INR Crore (rounded) |
| --- | --- | --- | --- |
| 1 | Mobilisation and site set-up | 2% | 2.97 |
| 2 | Piling and pile testing | 14% | 20.80 |
| 3 | Pile caps, grade beams and machine foundations | 12% | 17.83 |
| 4 | Superstructure: RCC frame and post-tensioned slabs | 34% | 50.52 |
| 5 | PEB roof and cladding | 12% | 17.83 |
| 6 | Industrial ground-floor slab | 8% | 11.89 |
| 7 | Finishes and waterproofing | 10% | 14.86 |
| 8 | External works | 5% | 7.43 |
| 9 | As-built documents, testing records and handover | 3% | 4.46 |
|  | Total | 100% | 148.60 |

# ANNEXURE D — APPLICABLE CODES, STANDARDS AND LAWS (AS AT BASE DATE)

The following are applicable as at the Base Date, together with any amendment, re-enactment or replacement, subject to Clause 15.

| Category | Reference |
| --- | --- |
| Structural design and loads | IS 456: 2000 – Plain and reinforced concrete IS 875 (Parts 1–5) – Design loads IS 1893 (Part 1): 2016 – Earthquake-resistant design IS 13920: 2016 – Ductile detailing IS 1343: 2012 – Prestressed concrete IS 800: 2007 – General construction in steel |
| Foundations and piling | IS 2911 (Part 1/Section 2): 2010 – Bored cast-in-situ piles IS 2911 (Part 4): 2013 – Load test on piles |
| Materials | IS 1786: 2008 – High-strength deformed steel bars IS 269: 2015 – Ordinary Portland cement IS 383: 2016 – Aggregates for concrete IS 10262: 2019 – Concrete mix proportioning IS 14268 – Uncoated stress-relieved low-relaxation strands |
| Building and fire | National Building Code of India 2016 Maharashtra Fire Prevention and Life Safety Measures Act, 2006 MIDC Development Control Regulations as applicable to the Site Unified Development Control and Promotion Regulations for Maharashtra State, 2020 (where applicable) |
| Labour and safety | Building and Other Construction Workers (Regulation of Employment and Conditions of Service) Act, 1996 Building and Other Construction Workers' Welfare Cess Act, 1996 Contract Labour (Regulation and Abolition) Act, 1970 Employees' Compensation Act, 1923 Minimum Wages Act, 1948 |
| Environment | Environment (Protection) Act, 1986 Construction and Demolition Waste Management Rules, 2016 Maharashtra Pollution Control Board consent conditions Central Ground Water Authority guidelines for dewatering |
| Tax | Central Goods and Services Tax Act, 2017 and Maharashtra Goods and Services Tax Act, 2017 Income-tax law (tax deducted at source) |
| Industry practice | Concrete Society Technical Report 34 (4th Edition) – Concrete industrial ground floors |

— End of document —